## Sheet1
Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT | Project :-41 COSMO NXT
Selected Group :- E BLDG LOBBY | Selected Group :- E BLDG LOBBY | Selected Group :- E BLDG LOBBY | Selected Group :- E BLDG LOBBY | Selected Group :- E BLDG LOBBY | Selected Group :- E BLDG LOBBY | Selected Group :- E BLDG LOBBY | Selected Group :- E BLDG LOBBY | Selected Group :- E BLDG LOBBY | Selected Group :- E BLDG LOBBY | Selected Group :- E BLDG LOBBY | Selected Group :- E BLDG LOBBY | Selected Group :- E BLDG LOBBY | Selected Group :- E BLDG LOBBY | Selected Group :- E BLDG LOBBY | Selected Group :- E BLDG LOBBY | Selected Group :- E BLDG LOBBY
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 725148 | E BLDG LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 0 | 702706 | 31 | 0 | [6 empty] | 0.0000
2 | 725149 | E BLDG 1ST FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725148 | 31 | 0 | [6 empty] | 0.0000
3 | 725150 | E BLDG 1ST FL. LOBBY OBD PAINT (M+L) | SQFT | 4764 | 4764 | 2 | 725149 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
4 | 725151 | E BLDG 1ST FL. LOBBY COURCE PUTTY (M+L) | SQFT | 4764 | 4764 | 2 | 725149 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
5 | 725165 | E BLDG 1ST FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725148 | 31 | 0 | [6 empty] | 0.0000
6 | 725166 | E BLDG 1ST FL. LOBBY OBD PAINT (M+L) | SQFT | 4764 | 4764 | 5 | 725165 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
7 | 725167 | E BLDG 1ST FL. LOBBY COURCE PUTTY (M+L) | SQFT | 4764 | 4764 | 5 | 725165 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
8 | 725168 | E BLDG 1ST FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725148 | 31 | 0 | [6 empty] | 0.0000
9 | 725169 | E BLDG 1ST FL. LOBBY OBD PAINT (M+L) | SQFT | 4764 | 4764 | 8 | 725168 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
10 | 725170 | E BLDG 1ST FL. LOBBY COURCE PUTTY (M+L) | SQFT | 4764 | 4764 | 8 | 725168 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
11 | 725171 | E BLDG 4TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725148 | 31 | 0 | [6 empty] | 0.0000
12 | 725172 | E BLDG 4TH FL. LOBBY OBD PAINT (M+L) | SQFT | 4764 | 4764 | 11 | 725171 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
13 | 725173 | E BLDG 4TH FL. LOBBY COURCE PUTTY (M+L) | SQFT | 4764 | 4764 | 11 | 725171 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
14 | 725174 | E BLDG 5TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725148 | 31 | 0 | [6 empty] | 0.0000
15 | 725175 | E BLDG 5TH FL. LOBBY OBD PAINT (M+L) | SQFT | 4764 | 4764 | 14 | 725174 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
16 | 725176 | E BLDG 5TH FL. LOBBY COURCE PUTTY (M+L) | SQFT | 4764 | 4764 | 14 | 725174 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
17 | 725177 | E BLDG 6TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725148 | 31 | 0 | [6 empty] | 0.0000
18 | 725178 | E BLDG 6TH FL. LOBBY OBD PAINT (M+L) | SQFT | 4764 | 4764 | 17 | 725177 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
19 | 725179 | E BLDG 6TH FL. LOBBY COURCE PUTTY (M+L) | SQFT | 4764 | 4764 | 17 | 725177 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
20 | 725180 | E BLDG 7TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725148 | 31 | 0 | [6 empty] | 0.0000
21 | 725181 | E BLDG 7TH FL. LOBBY OBD PAINT (M+L) | SQFT | 4764 | 4764 | 20 | 725180 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
22 | 725182 | E BLDG 7TH FL. LOBBY COURCE PUTTY (M+L) | SQFT | 4764 | 4764 | 20 | 725180 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
23 | 725183 | E BLDG 8TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725148 | 31 | 0 | [6 empty] | 0.0000
24 | 725184 | E BLDG 8TH FL. LOBBY OBD PAINT (M+L) | SQFT | 4764 | 4764 | 23 | 725183 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
25 | 725185 | E BLDG 8TH FL. LOBBY COURCE PUTTY (M+L) | SQFT | 4764 | 4764 | 23 | 725183 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
26 | 725186 | E BLDG 9TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725148 | 31 | 0 | [6 empty] | 0.0000
27 | 725187 | E BLDG 9TH FL. LOBBY OBD PAINT (M+L) | SQFT | 4764 | 4764 | 26 | 725186 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
28 | 725188 | E BLDG 9TH FL. LOBBY COURCE PUTTY (M+L) | SQFT | 4764 | 4764 | 26 | 725186 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
29 | 725189 | E BLDG 10TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725148 | 31 | 0 | [6 empty] | 0.0000
30 | 725190 | E BLDG 10TH FL. LOBBY OBD PAINT (M+L) | SQFT | 4764 | 4764 | 29 | 725189 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
31 | 725191 | E BLDG 10TH FL. LOBBY COURCE PUTTY (M+L) | SQFT | 4764 | 4764 | 29 | 725189 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
32 | 725192 | E BLDG 11TH REFF. FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725148 | 31 | 0 | [6 empty] | 0.0000
33 | 725193 | E BLDG 11TH REFF. FL. LOBBY OBD PAINT (M+L) | SQFT | 4764 | 4764 | 32 | 725192 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
34 | 725194 | E BLDG 11TH REFF. FL. LOBBY COURCE PUTTY (M+L) | SQFT | 4764 | 4764 | 32 | 725192 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
35 | 725195 | E BLDG 12TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725148 | 31 | 0 | [6 empty] | 0.0000
36 | 725196 | E BLDG 12TH FL. LOBBY OBD PAINT (M+L) | SQFT | 4764 | 4764 | 35 | 725195 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
37 | 725197 | E BLDG 12TH FL. LOBBY COURCE PUTTY (M+L) | SQFT | 4764 | 4764 | 35 | 725195 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
38 | 725198 | E BLDG 13TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725148 | 31 | 0 | [6 empty] | 0.0000
39 | 725199 | E BLDG 13TH FL. LOBBY OBD PAINT (M+L) | SQFT | 4764 | 4764 | 38 | 725198 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
40 | 725200 | E BLDG 13TH FL. LOBBY COURCE PUTTY (M+L) | SQFT | 4764 | 4764 | 38 | 725198 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
41 | 725201 | E BLDG 14TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725148 | 31 | 0 | [6 empty] | 0.0000
42 | 725202 | E BLDG 14TH FL. LOBBY OBD PAINT (M+L) | SQFT | 4764 | 4764 | 41 | 725201 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
43 | 725203 | E BLDG 14TH FL. LOBBY COURCE PUTTY (M+L) | SQFT | 4764 | 4764 | 41 | 725201 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
44 | 725204 | E BLDG 15TH REFF. FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725148 | 31 | 0 | [6 empty] | 0.0000
45 | 725205 | E BLDG 15TH REFF. FL. LOBBY OBD PAINT (M+L) | SQFT | 4764 | 4764 | 44 | 725204 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
46 | 725206 | E BLDG 15TH REFF. FL. LOBBY COURCE PUTTY (M+L) | SQFT | 4764 | 4764 | 44 | 725204 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000
47 | 725207 | E BLDG 16TH FL. LOBBY | Dz 12nos) | 0.0000 | 0.0000 | 1 | 725148 | 31 | 0 | [6 empty] | 0.0000
48 | 725208 | E BLDG 16TH FL. LOBBY OBD PAINT (M+L) | SQFT | 4764 | 4764 | 47 | 725207 | 4 | 93886 | OBD PAINT (M+L) | [5 empty] | 0.0000
49 | 725209 | E BLDG 16TH FL. LOBBY COURCE PUTTY (M+L) | SQFT | 4764 | 4764 | 47 | 725207 | 4 | 93889 | COURCE PUTTY (M+L) | [5 empty] | 0.0000